# PISES NEW CAMPUS – AL SAFA

## EXECUTIVE DEVELOPMENT PRESENTATION

Capacity Target: 7,000 Students
Plot Area: 25,000 sqm
Configuration: 3 Floors + 1 Basement
Projected GBA: ~60,000 sqm

# 1. THE STRATEGIC CONTEXT

PISES requires a purpose-built, regulation-compliant campus capable of serving 7,000 students within Riyadh’s urban constraints.

This development is designed to: • Eliminate long-term capacity pressure
• Replace fragmented expansion strategy
• Deliver full academic ecosystem
• Align with TBC Category A standards
• Create a 30+ year institutional asset

# 2. CLASSROOM NEEDS – THE BASIS

## Regulatory Basis

• TBC Category A – Maximum 25 students per classroom
• Planning model used: 22 students average
• Net classroom area benchmarked to TBC requirements

## Projected Classroom Requirement (7,000 Model)

| Section | Classrooms |
| --- | --- |
| Early Years | 48 |
| Primary | 99 |
| Lower Secondary | 103 |
| Upper Secondary | 67 |

Total Standard Classrooms: 317

Net Classroom Area ≈ 22,700 sqm

This forms the academic backbone of the campus.

# 3. SPECIALIST ACADEMIC REQUIREMENTS

A 7,000-student school cannot operate on classrooms alone.

## Required Facilities

• 18 Science Laboratories
• 13 ICT / Robotics Labs
• 2 Main Libraries + Digital Research Rooms
• 8 Art Studios
• 6 Music Rooms + Practice Pods
• 1 Auditorium (1,000–1,200 capacity)
• 1 Indoor Sports Hall
• Staff academic work hubs

Total Specialist Net Area ≈ 10,580 sqm

# 4. SEN & WELLBEING FRAMEWORK

Inclusion capacity planned for 8–12% of student body.

Includes: • SEN resource rooms
• Therapy & counselling rooms
• Sensory regulation spaces
• Student wellbeing hubs (per wing)
• Medical clinics

Total SEN & Wellbeing Net Area ≈ 1,274 sqm

# 5. TOTAL NET ACADEMIC AREA

| Component | Net Area (sqm) |
| --- | --- |
| Classrooms | 22,700 |
| Specialist Spaces | 10,580 |
| SEN & Wellbeing | 1,274 |

Total Academic Net Area ≈ 34,554 sqm

# 6. NET-TO-GROSS & TOTAL BUILDING AREA

Planning Efficiency Factor: 1.45

Academic Gross Area ≈ 50,000–52,000 sqm Additional Support Gross (Admin, cafeteria, plant, prayer, storage) ≈ 9,000 sqm

Total Projected Gross Built-Up Area ≈ 59,000–61,000 sqm

Target Planning Value: ~60,000 sqm

# 7. SITE & COVERAGE STRATEGY

Plot Size: 25,000 sqm Target Building Footprint: ≤ 17,500 sqm Coverage Ratio: 65–72%

Remaining Site Allocated To: • Multi-use football field
• Outdoor courts
• Early years play zones
• Emergency assembly areas
• Drop-off loops
• Landscape buffers

Basement required for parking + plant.

# 8. PARKING & TRAFFIC MODEL

Estimated Staff: 600–750
Required Parking: 750–800 spaces

Parking Strategy: • Basement majority
• Limited surface visitor parking

Bus Strategy: • 35–45% bus usage
• ~70 buses (staggered model)

Traffic separation required for: • Primary
• Boys Secondary
• Girls Secondary
• Service access

# 9. HIGH-LEVEL COST ESTIMATE

Projected GBA: ~60,000 sqm

Riyadh Education Build Cost Benchmark: SAR 3,000 – 4,500 per sqm (mid specification)

## Estimated Construction Cost Range:

Low Range: 60,000 × 3,000 = SAR 180M
Mid Range: 60,000 × 3,750 ≈ SAR 225M
Upper Range: 60,000 × 4,500 = SAR 270M

Excludes: • Land cost
• Financing cost
• External consultant fees

Basement parking and auditorium are major cost drivers.

# 10. DEVELOPMENT STAGES

## Stage 1 – Concept Validation (3–4 months)

• Architect appointment
• Traffic modelling study
• Fire consultant modelling
• Concept freeze

## Stage 2 – Detailed Design (6–8 months)

• Full architectural design
• Structural & MEP design
• Authority submissions
• Tender documentation

## Stage 3 – Tender & Award (3–4 months)

• Contractor prequalification
• Tender issue & evaluation
• Award & mobilization

## Stage 4 – Construction (18–24 months)

• Basement works
• Superstructure
• Envelope & MEP
• Fit-out & commissioning

Total Project Duration (Realistic): 30–36 months

# 11. OPTIONAL PHASING STRATEGY

If required:

Phase 1: 5,500–6,000 student capacity
Phase 2: Expansion to 7,000

Core infrastructure sized for full 7,000 from day one.

# 12. KEY DECISIONS REQUIRED

SMC / Embassy must confirm: • Target capacity fixed at 7,000?
• Single-phase vs phased build?
• Budget ceiling?
• Architect RFP authorization?
• Traffic & fire study commissioning?

# 13. CONCLUSION

The 7,000-student campus is technically feasible on 25,000 sqm.

Feasibility depends on: • Controlled footprint
• Basement parking implementation
• Efficient circulation design
• Compact external sports model

This development establishes: • Institutional stability
• Regulatory compliance
• Long-term academic infrastructure
• A 30+ year strategic educational asset

# OPTIONAL SLIDE – CONSTRUCTION COST STRUCTURE EXPLAINED

## What is Included in Each Cost Layer?

### 1. Core & Shell (C&S)

Includes: • Foundations & structural frame
• Slabs, beams, columns
• Roof structure & waterproofing
• External walls & façade
• Windows & external doors
• Stair cores & lift shafts
• Main utility rooms & vertical shafts

This stage delivers a weather-tight structural building.

### 2. First Fix (Hidden Services)

Includes: • Electrical conduits & cabling infrastructure
• AC ducting & chilled water piping
• Plumbing pipework
• Fire sprinkler network
• Data cabling pathways

Services are concealed before wall & ceiling closure.

### 3. Second Fix (Visible Fit-Out)

Includes: • Light fixtures, switches, sockets
• AC diffusers & FCUs
• Plumbing fixtures (WC, basins)
• Internal doors & joinery
• Floor finishes & ceiling systems

Rooms become operational at this stage.

### 4. Third Fix / Specialist Fit-Out

Includes: • Smart boards & AV systems
• Lab benches & fume hoods
• Library shelving
• Auditorium seating & stage systems
• Furniture

This layer drives variability in final cost.

============================================================= OPTIONAL SLIDE – COST ESTIMATE BY ROOM TYPE =============================================================

(All figures indicative – Riyadh 2026 mid-spec benchmark)

## 1. STANDARD CLASSROOM (75 sqm – Secondary)

| Component | Estimated Cost (SAR) |
| --- | --- |
| Core & Shell | 120,000 – 150,000 |
| First Fix | 35,000 – 45,000 |
| Second Fix & Finishes | 55,000 – 75,000 |
| Third Fix (AV + Furniture) | 30,000 – 45,000 |
| Total per Classroom | 240,000 – 315,000 |

## 2. SCIENCE LABORATORY (100 sqm)

| Component | Estimated Cost (SAR) |
| --- | --- |
| Core & Shell | 170,000 – 200,000 |
| First Fix (Heavy MEP) | 75,000 – 95,000 |
| Second Fix | 100,000 – 130,000 |
| Third Fix (Benches + Equipment) | 130,000 – 180,000 |
| Total per Lab | 475,000 – 605,000 |

Labs cost approximately 2x standard classroom due to MEP intensity.

## 3. ICT / ROBOTICS LAB (80 sqm)

| Component | Estimated Cost (SAR) |
| --- | --- |
| Core & Shell | 135,000 – 160,000 |
| First Fix | 50,000 – 65,000 |
| Second Fix | 65,000 – 85,000 |
| Third Fix (IT + Furniture) | 70,000 – 110,000 |
| Total per ICT Lab | 320,000 – 420,000 |

## 4. AUDITORIUM (1,200 sqm)

| Component | Estimated Cost (SAR) |
| --- | --- |
| Core & Shell | 3.0 – 3.5 M |
| MEP Systems | 1.2 – 1.5 M |
| Seating & Acoustics | 2.0 – 3.0 M |
| Stage & AV Systems | 1.5 – 2.0 M |
| Total Auditorium | 7.5 – 10 M SAR |

## 5. INDOOR SPORTS HALL (1,200 sqm)

| Component | Estimated Cost (SAR) |
| --- | --- |
| Core & Shell | 2.5 – 3.0 M |
| MEP & Ventilation | 1.0 – 1.3 M |
| Sports Flooring | 0.8 – 1.2 M |
| Equipment & Storage | 0.7 – 1.0 M |
| Total Sports Hall | 5.0 – 6.5 M SAR |

## COST SUMMARY PER SQM (REFERENCE)

| Stage | SAR / sqm (Indicative) |
| --- | --- |
| Core & Shell | 1,600 – 2,100 |
| First Fix | 500 – 700 |
| Second Fix | 700 – 1,000 |
| Third Fix | 400 – 700 |
| Total Mid-Spec Range | 3,200 – 4,500 SAR / sqm |

Applied to ~60,000 sqm GBA:

Low Range ≈ SAR 180M
Mid Range ≈ SAR 225M
Upper Range ≈ SAR 270M

============================================================= OPTIONAL SLIDE – PROJECT TIMELINE & STAGES =============================================================

Total Estimated Duration: 30–36 Months

STAGE 1 – Concept & Validation (0–4 Months) • Architect appointment
• Traffic & fire modelling
• Concept design freeze
• Budget validation
• Authority pre-consultation

STAGE 2 – Detailed Design & Approvals (5–12 Months) • Full architectural & engineering design
• Structural & MEP coordination
• Cost plan refinement
• Authority submissions & approvals
• Tender documentation preparation

STAGE 3 – Tender & Award (13–16 Months) • Contractor prequalification
• Tender issue
• Technical & financial evaluation
• Contract award & mobilization

STAGE 4 – Construction (17–36 Months) • Basement works (Months 17–22)
• Superstructure (Months 20–28)
• Envelope & MEP installation (Months 24–32)
• Internal fit-out (Months 28–35)
• Testing & commissioning (Months 34–36)

Target Opening: Month 36

============================================================= OPTIONAL SLIDE – FINANCING DRAW-DOWN MODEL =============================================================

Assumed Project Value (Mid Case): SAR 225M
Construction Period: 24 Months
Design & Preconstruction: 12 Months

Typical Drawdown Distribution (Education Build Model)

Year 1 (Design & Early Works) – 10–15% ≈ SAR 22M – 34M

Year 2 (Basement + Structure Peak) – 35–40% ≈ SAR 79M – 90M

Year 3 (Fit-Out & Completion) – 40–45% ≈ SAR 90M – 101M

Retention / Final Payments – 5% ≈ SAR 11M

Cashflow Curve Characteristics

• Low initial burn during design
• Sharp increase during structural phase
• Highest monthly burn during MEP & fit-out overlap
• Final taper during commissioning

Peak Monthly Burn (Estimated): SAR 12M – 15M per month during peak construction

FINANCING OPTIONS

Option A – Full Capital Funding (SMC/Embassy Backed) Option B – Bank Project Financing (Construction Loan) Option C – Phased Funding (6,000 → 7,000 expansion) Option D – Hybrid Lease-Back Structure

Debt servicing stress depends on: • Tuition revenue projections
• Phasing model
• Interest rate environment

============================================================= END OF EXECUTIVE PRESENTATION ————————————————————- ————————————————————-